## Timeline
Be-A-Mazed
| Task |  | Start date | Due date | Person | Additional info
| Research MMOGs |  | 2019-09-23 | 2019-10-03 | All
| Agree on coding styles |  | 2019-09-27 | 2019-10-03 | All
| Game decisions |  | 2019-09-23 | 2019-10-03
|  | Finalise Game idea / narrative | 2019-09-23 | 2019-10-03 | All | Create game description
|  | Goal / how do they win | 2019-09-23 | 2019-10-03
|  | Rules / Restrictions | 2019-09-23 | 2019-10-03
|  | Interaction | 2019-09-23 | 2019-10-03
|  | Colour theme | 2019-09-23 | 2019-10-03
|  | Font styles | 2019-09-23 | 2019-10-03
|  | Game objects | 2019-09-23 | 2019-10-03
|  | Sounds | 2019-09-23 | 2019-10-03
|  | Controls | 2019-09-23 | 2019-10-03
|  | Game Play | 2019-09-23 | 2019-10-03
|  | Levels | 2019-09-23 | 2019-10-03
| HTML5 code |  | 2019-09-23 | 2019-11-25
|  | HTML tasks… | 2019-09-23 | 2019-11-25
|  | HTML tasks… | 2019-09-23 | 2019-11-25
|  | HTML tasks… | 2019-09-23 | 2019-11-25
|  | HTML tasks… | 2019-09-23 | 2019-11-25
| CSS code |  | 2019-09-23 | 2019-11-25
|  | CSS tasks… | 2019-09-23 | 2019-11-25
|  | CSS tasks… | 2019-09-23 | 2019-11-25
|  | CSS tasks… | 2019-09-23 | 2019-11-25
|  | CSS tasks… | 2019-09-23 | 2019-11-25
| JavaScript code |  | 2019-10-03 | 2019-11-01
|  | JavaScript tasks | 2019-10-03 | 2019-11-01
|  | JavaScript tasks | 2019-10-03 | 2019-11-01
|  | JavaScript tasks | 2019-10-03 | 2019-11-01
|  | JavaScript tasks | 2019-10-03 | 2019-11-01
Testing
Data Management
Flow control
Server-client management
Deployment plan
Security
| Finalise game |  |  | 2019-11-15 | All
| YouTube trailer |  |  | 2019-11-18
| Report |  |  | 2019-11-20 | All
| Compile files / repo |  |  |  | All
| Assignment due |  |  | 2019-11-22 | All

## Team Meetings
Be-A-Mazed
| Date | Time | Attendees | Topics discussed | Actions going forward
| 2019-09-20 | 13:00 | LK, NA, HG | Game ideas, meeting times | Meet on weekly basis at set time (Fri 12noon), twice if necessary (flexible depending on schedules) Research game ideas, research MMOGs, investigate GitHub, individual study on HTML, CSS and JavaScript,
| 2019-09-26 | 13:00 | LK,NA | Looked at GitHub | Research game ideas further, research MMOGs, investigate GitHub, individual study on HTML, CSS and JavaScript
| 2019-09-27 | 13:00 | LK,NA | GitHub progress | As above

## Coursework Checklist
Ongoing Maintenance (week by week)
Each team member is contributing (commits, updates, testing)
Bugs, features, releases are reguarly updated
Meetings, tasks, issues, information, are logged (record so you remember)
Does the team work synergistically?
Type of game
Team details submitted to lecture
Plan/objectives (milestones/dates)
Organise this on github (readme)
Team members (usernames, ..) all added to project
Coding styles, (agreed and consistent)
Meeting dates (plan/backup)
Code validation/testing plan (automated vs user)
Manage code changes/versions (different file types/bugs/tasks)
Open source practices (real-world)
Mechanics of the game (client side)
Game play details
Scoring/point system
Animation/required graphics/code
User input/controls
Interaction environment/collisions
Testing
Usability (view/design/..)
Working client implementation (standalone) (offline sandpit version?)
Could the game run standalone with no other players? (e.g., early testing)
Javascript/DOM/CSS/html (validation/sanity checks)
Data Management
Separating data (temporary data, data for client and server/structured/managed) e.g., which information needs to be sent/received from the server, which is created/managed locally
Flow control
Login/temp visitor
Restarting/joining exiting game
Managing resources/partitioning (groups/levels/regions)
Server-client management
Passing data to-from the server in real time
Suitable language/data transmission format e.g., time information, other user status information,
Server data storage (sql/mysql/litesql/..)
Deployment plan
How will it be deployment testing be done
Is the GitHub project easy to deploy and test (outside user/community/guidance information/ rules/settings/robust)?
Deployment criteria clear (libraries, server permissions, defined)
Is there a list of active tests, success, Q&A for the deployment of the project?
Security
Validate data/user information
Security/safety/backups
Optimization
Slow connections, crashes, different browsers,
Optimizing javascript code/graphics/design
Compression (file/data formats, jpg vs png vs bmp, zlib, ..)
Library/log
How many lines of code have been written by each team member?
How many external files/libraries have been used? (clearly explained)
How many external assets (images/sounds)?
What are the game limitations?